## Feuille 1
| Status | Attributed to : | 07.05-13.05 | 14.05-20.05 | 21.05-27.05 | 28.05-03.06 | 04.06-10.06 | 11.06-17.06 | 18.06-24.06 | 25.06-01.07 | 02.07-08.07 | 09.07-12.07
Tasks
Hardware
Gather Information about Mechanics, robotics.. To make efficient first prototype. | Done | Yin, Kevin , Robert, Vera
Decide Robot design (first prototype) | Done | ALL
Brainstorm System Architectures | Done | Yessmine
Build an efficient Prototype | Done | Yin, Kevin , Robert
Decide primary System Architecture | Done | ALL
Refine Robot Design | Done | Vera, Robert
Upkeep and last adjustments | Done | Vera, Robert, Kevin, Yin
Software
Gather broad knowledge about RL Algorithms and how to implement them | Done | Vera , Zied
Brainstorm reward Function | Done | ALL
Select RL Algorithm | Done | Yessmine, Zied, Yin
Implement RL Algorithm | Done | Yessmine, Zied
Improve RL Algorithm |  | Zied, Yessmine
Refine and test the reward function |  | Zied, Yessmine
Understand C++ Library | Done | ALL
Add more required functions to buildhat library | Done | Yin, Kevin, Robert
Clean up code and make last adjustments |  | ALL
Program remote control | Done | Kevin, Yin, Robert, Vera
Program Agent | Doing | Vera, Zied
Write Tests | Doing | ALL
General
Define Requierments | Done | ALL
Train Agent | Doing | Yessmine, Robert
Collect training Data | Doing | Kevin, Vera
Define Observation Space (decide which sensors to use and how) | Done | Zied, Yessmine
Define Action Space (Define type of action) | Done | Zied, Yessmine
Refine and Adapt Environment, Rewards, Spaces and States |  | Zied, Yessmine
Documentation |  | ALL
Preparation of final presentation |  | ALL
CI Pipeline | Done | Yessmine
Video |  | Kevin, Robert, Zied
Poster |  | Vera, Yessmine, Yin