## Feuille 1
Time | 07.05 - 13.05 | 14.05 - 03.06 | 04.06 - 01.07 | 02.07 - 11.07
Tasks
Gather Information about Mechanics, robotics.. To make efficient first prototype.
Decide Robot design
Understand C++ Library
Gather broad knowledge about RL Algorithms and how to implement them
Brainstorm System Architectures
Build an efficient Prototype
Try out some RL Algorithms (implementation and testing)
Decide System Architecture
Train Agent
Improve RL Algorithm