## Feuille 1
| Status | Attributed to : | 07.05-13.05 | 14.05-20.05 | 21.05-27.05 | 28.05-03.06 | 04.06-10.06 | 11.06-17.06 | 18.06-24.06 | 25.06-01.07 | 02.07-08.07 | 09.07-12.07
Tasks
Hardware
Gather Information about Mechanics, robotics.. To make efficient first prototype. | Done | Yin, Kevin , Robert
Decide Robot design (first prototype) | Done | ALL
Brainstorm System Architectures | Done | Yessmine
Build an efficient Prototype | Done | Yin, Kevin , Robert
Decide primary System Architecture | Done | ALL
Refine Robot Design | Done
Upkeep and last adjustments
Software
Gather broad knowledge about RL Algorithms and how to implement them | Done | Vera , Zied
Brainstorm reward Function | Done | ALL
Select RL Algorithm | Doing
Implement RL Algorithm
Improve RL Algorithm
Refine and test the reward function
Understand C++ Library | Doing | ALL
Add more required functions to buildhat library
Adjust Algorithm as needed
Clean up code and make last adjustments
General
Define Requierments | Done | ALL
Train Agent
Define Observation Space (decide which sensors to use and how) | Doing | Zied, Yesmine
Define Action Space (Define type of action) | Doing | Zied, Yesmine
Refine and Adapt Environment, Rewards, Spaces and States